## Shared Components
Component Name | Page(s) Used | Component Type | Description | Milestone | Priority | Time Estimate (days) | Status
Navbar – Top Navigation Bar | All Pages | Shared | Header with search, profile, navigation breadcrumbs | Global | High | 1.5 | Not Started
Sidebar – Main Navigation Panel | All Pages | Shared | Collapsible vertical navigation with icons, labels | Global | High | 2 | Not Started
Sidebar – Expand/Collapse Toggle | All Pages | Shared | Button to toggle sidebar width, shows only icons when collapsed | Global | High | 0.5 | Not Started
Dropdown Menu | All filters, inputs | Shared | Standard dropdown with support for dependency logic (e.g., city depends on country) | M1 – Setup | High | 0.25 | Not Started
Filter Panel | Crop Selection, Sales Views, Production View | Shared | Container for multiple filters (dropdowns, sliders, toggles) | M1 – Setup | High | 1.5 | Not Started
Date/Week Selector | Production View, Sales Simulator | Shared | Horizontal scrollable bar for W12–W29 weekly views | M2 – Production | High | 1.5 | Not Started
Table/Grid Layout | Crop/Client Views, Task Schedule | Shared | Responsive grid for weekly schedule, sortable/filterable | M2 – Production | High | 2 | Not Started
Modal Window | Task Editor, Weather Detail, Insights | Shared | Reusable modal for popups across features | M2 – Production | Medium | 1 | Not Started
Interactive Map | Plot Locating, Final Plot Overview | Shared | Polygon drawing, hoverable zones, overlays | M1 – Setup | High | 2.5 | Not Started
Tabs/Toggle Panel | Crop View, Client View, Task Modal | Shared | Toggles to switch metrics or views | M2 – Production | Medium | 1 | Not Started
Progress/Score Bars | Crop Selection, Crop Details, Sales | Shared | Horizontal bar for agricultural, environmental, economic scoring | M1 – Setup | Medium | 1 | Not Started
Notification/Alert Banner | Crop Details, Agronomic Warning | Shared | Visual alerts for AI recommendations, validation errors | M2 – Production | Medium | 1 | Not Started
Dropdown – Plot Selector | Farm Setup, Production | Shared | Dropdown to select plot, used to filter plots and manage views | M1 – Setup | High | 0.5 | Not Started
Dropdown – Crop Selector | Farm Setup, Sales | Shared | Used to filter by crop across selection, insights, and orders | M1 – Setup | High | 0.5 | Not Started
Dropdown – Task Filter | Production | Shared | Dropdown to filter tasks (irrigation, hygiene, etc.) in planner | M2 – Production | Medium | 0.5 | Not Started
Dropdown – Order Type | Sales | Shared | Dropdown for order channel type: shop, institutional, box | M3 – Sales | Medium | 0.5 | Not Started
Dropdown – Promotion Type | Sales | Shared | Multi-select dropdown for discounts, bundles, etc. | M3 – Sales | Medium | 0.5 | Not Started
Schedule Grid (Weekly Planner) | Production, Sales, Crop Details | Shared | Weekly table layout for visualizing growth stages, tasks, forecasts, and metrics | M2 – Production | High | 2.5 | Not Started
Simulated Bar Chart | Harvest Simulator (Production), Sales Simulator | Shared | Multi-color bar showing yield/surplus/waste dynamically based on simulator input | M2/M3 | High | 1.5 | Not Started
Agricultural Indicator Icon | Crop Details, Harvest Sim., Sales | Shared | Semi-circular icon + label representing farming requirements/risks | M1 – Setup | Medium | 0.5 | Not Started
Environmental Indicator Icon | Crop Details, Harvest Sim., Sales | Shared | Semi-circular icon + label showing sustainability/impact | M1 – Setup | Medium | 0.5 | Not Started
Economical Indicator Icon | Crop Details, Harvest Sim., Sales | Shared | Semi-circular icon + label showing cost/profit/revenue trends | M1 – Setup | Medium | 0.5 | Not Started
Hover Interaction – Growth Stage | Crop Details, Weekly Planner | Shared | Tooltip or overlay on growth stage cells to show detailed stage data | M1 – Setup | Medium | 0.5 | Not Started
Arrows – Navigation Controls | All paginated or stepped sections | Shared | Forward/backward buttons to scroll week, pages, or blocks | Global | High | 0.5 | Not Started
Indicator Toggle (show/ hide) | Production Planner, Crop Map Overview, Sales | Shared | Icons with toggle behavior for displaying machine work, irrigation, disease, etc. | M2 – Production | Medium | 1 | Not Started
Selected Filters Chips | Sales Simulator, Crop Assignment, Weekly View | Shared | Clickable/removable chips to show current filter state (e.g., crop = broccoli, plot = NL, P1.1) | M2/M3 | Medium | 0.5 | Not Started

## Production Management
Component Name | Page(s) Used | Component Type | Description | Milestone | Priority | Time Estimate (days) | Status
Sidebar Navigation | All production pages | Shared | Vertical navigation panel with icons and labels, collapsible to icon-only view | Global | High | 2 | Not Started
Top Navigation Bar | All production pages | Shared | Header with section switch (Production/Sales), search bar, and profile settings | Global | High | 1.5 | Not Started
Dropdown – Plot Filter | All production pages with week scrollers | Shared | Filter to select specific plot(s) | M2 – Production | High | 0.5 | Not Started
Dropdown – Crop Filter | All production pages with week scrollers | Shared | Filter to choose one or more crops | M2 – Production | High | 0.5 | Not Started
Dropdown – Task Filter | All production pages with week scrollers | Shared | Filter dropdown to show specific task types (e.g. irrigation, harvest) | M2 – Production | Medium | 0.5 | Not Started
Schedule Grid Table | All production pages with week scrollers | Shared | Horizontal week headers + vertical task/crop rows with colored cells | M2 – Production | High | 2.5 | Not Started
Week Navigation Arrows | All production pages with week scrollers | Shared | Circular arrow buttons to scroll or navigate between week ranges | M2 – Production | High | 0.5 | Not Started
Growth Stage Color Cell | All production pages with week scrollers | Shared | Background-colored cells showing crop stage (seedling, ripening, etc.) | M2 – Production | High | 0.5 | Not Started
Task Icon Overlay | All production pages with week scrollers | Shared | Icons representing scheduled task type on timeline cells (e.g., 💧🛡️✂️) | M2 – Production | High | 0.5 | Not Started
Tooltip on Hover (Growth & Task) | All production pages with week scrollers | Shared | Tooltip to show details when hovering task or growth stage cells | M2 – Production | Medium | 0.5 | Not Started
Indicator Toggle Panel ("Show:") | All production pages with week scrollers | Shared | Icon toggle panel to show/hide overlays (e.g. irrigation, disease, machine work) | M2 – Production | Medium | 1 | Not Started
Weather Overview Strip | Weekly Weather Forecast | Shared | Two horizontal bar gradients showing temperature & precipitation forecast | M2 – Production | Medium | 1 | Not Started
Weather Details Panel | Daily Weather Forecast | Shared | Detailed weather view per day: temp, humidity, rainfall, wind | M2 – Production | Medium | 1 | Not Started
Simulator Bar (Harvest/Prod.) | Harvest Simulator, Sales Simulator | Shared | Visual bar chart with expected yield (green), surplus (blue), waste (red) | M2 – Production | High | 1.5 | Not Started
Agricultural Indicator | Weekly View, Simulator | Shared | Semi-circular arc showing agronomic suitability (soil, crop health) | M2 – Production | Medium | 0.5 | Not Started
Environmental Indicator | Weekly View, Simulator | Shared | Semi-circular arc showing water, pesticide, emissions risk | M2 – Production | Medium | 0.5 | Not Started
Economic Indicator | Weekly View, Simulator | Shared | Semi-circular arc showing profitability vs. loss tradeoffs | M2 – Production | Medium | 0.5 | Not Started
Filter Chips (Selected Filters) | Simulator, Weather Forecast | Shared | UI chips that show and allow removing active filters | M2 – Production | Medium | 0.5 | Not Started
Modal Container | Weather, Task Details, Simulator | Shared | Generic modal used for overlays/popups with backdrop and close button | M2 – Production | High | 1 | Not Started
Sticky Column Wrapper | Weekly View, Weather, Simulator | Shared | Locks crop/task columns on scroll to keep row labels visible | M2 – Production | Medium | 0.5 | Not Started
Legend / Color Key | Weekly View, Weather, Simulator | Shared | Explains color stages and task icons for crop stages or risk levels | M2 – Production | Medium | 0.5 | Not Started
Indicator Toggle Panel – Production View | Weekly Production View | Shared | A horizontal row of toggleable icons to show/hide overlays: weather, tasks, demand, loss, sort | M2 – Production | High | 1 | Not Started

## Sales Management
Component Name | Page(s) Used | Component Type | Description | Milestone | Priority | Time Estimate (days) | Status
Sidebar Navigation | All pages | Shared | Vertical navigation menu with icons and labels (Farm, Sales, Production...), collapsible | Global | High | 2 | Not Started
Top Navigation Bar | All pages | Shared | Header with toggle for Production/Sales views, search bar, and user profile | Global | High | 1.5 | Not Started
Dropdown – Crops Filter | All sales pages | Shared | Dropdown to filter sales data by crop | M3 – Sales | High | 0.5 | Not Started
Dropdown – Orders Filter | All sales views | Shared | Dropdown to filter by order type (confirmed, potential, expected) | M3 – Sales | Medium | 0.5 | Not Started
Dropdown – Promotions Filter | All sales views | Shared | Filter to select promo type: discount, flash, referral, etc. | M3 – Sales | Medium | 0.5 | Not Started
Dropdown – Clients Filter | All sales views | Shared | Filter to select client segment/persona (VIP, retailer, young shoppers...) | M3 – Sales | Medium | 0.5 | Not Started
Forecast Bars – Demand/Price | Crop View, Client View | Shared | Weekly gradient bar showing predicted demand and price fluctuation | M3 – Sales | Medium | 1 | Not Started
Week Navigation Arrows | All sales views | Shared | Controls to navigate week numbers horizontally across the timeline | M3 – Sales | High | 0.5 | Not Started
Sales Schedule Grid | All sales views | Shared | Grid table with weeks (columns) and sales metrics (rows) | M3 – Sales | High | 2 | Not Started
Tooltip on Hover (Grid/Icons) | All timeline grids | Shared | Tooltip to explain cell metrics or indicators (e.g., promo %, order status) | M3 – Sales | Medium | 0.5 | Not Started
Indicators Toggle Panel ("Show:") | All sales views | Shared | Toggle to show/hide rows: quantity, revenue, promo, mix, orders, etc. | M3 – Sales | High | 1 | Not Started
Legend / Icon Key | All timeline views | Shared | Icon and label list for interpreting cell content (confirmed, promo, revenue...) | M3 – Sales | Medium | 0.5 | Not Started
Filter Chips – Selected Filters | Crop View, Client View, Simulator | Shared | Visual chips showing active filters (e.g., Broccoli, Retailer), removable | M3 – Sales | Medium | 0.5 | Not Started
Simulator Bar – Sales Forecast | Sales Simulator | Shared | Color bar: green (expected sales), blue (inventory), red (waste), with price slider | M3 – Sales | High | 1.5 | Not Started
Agricultural Indicator | Sales Simulator | Shared | Semi-circular icon showing agronomic relevance or impact | M3 – Sales | Medium | 0.5 | Not Started
Environmental Indicator | Sales Simulator | Shared | Sustainability impact of sales strategy (e.g., irrigation waste) | M3 – Sales | Medium | 0.5 | Not Started
Economic Indicator | Sales Simulator | Shared | Profitability under current price/promo scenario | M3 – Sales | Medium | 0.5 | Not Started
Metric Row Icons (Toggleable) | All sales views (Crop + Client tabs) | Shared | Icons for rows: Confirmed Orders, Revenue, Crop Mix, etc. controlled via toggle or icon tap | M3 – Sales | Medium | 1 | Not Started
Client Insight Panel | Client View, Client Details | Shared | Header insight box showing total demand, stock, fulfillment, price sensitivity, churn risk | M3 – Sales | Medium | 1 | Not Started
Crop Insight Panel | Crop View, Crop Details | Shared | Header insight box showing stock, demand, price forecast, promo alerts | M3 – Sales | Medium | 1 | Not Started
Modal Container | Sales Simulator | Shared | Reusable modal for simulator interface | M3 – Sales | High | 1 | Not Started

## Farm Setup
Component Name | Page(s) Used | Component Type | Description | Milestone | Priority | Time Estimate (days) | Status
Map Pin + Polygon Form | Plot Locating | Page-Specific | Draw/select plot on map, calculate area, altitude | M1 – Setup | High | 2 | Not Started
Zone Splitter | Plot Division | Page-Specific | Manual input fields for zone dimension and ID | M1 – Setup | Medium | 1 | Not Started
Bed Structuring Form | Zone Structuring | Page-Specific | Inputs for bed width, length, spacing, and bed type | M1 – Setup | Medium | 1 | Not Started
Crop Card Gallery | Crop Selection | Page-Specific | Card view with crop image, score, seed price, recommendation tag | M1 – Setup | Medium | 2 | Not Started
Crop Info Accordion | Crop Details | Page-Specific | Expandable sections: growth, germination, spacing, alerts | M1 – Setup | Medium | 1.5 | Not Started
Validation Warning Popup | Agronomic Warning | Page-Specific | Popup that warns user about yield impact due to changes | M1 – Setup | Medium | 1 | Not Started
Planting Map Overlay | Assign Crops to Fields | Page-Specific | Interactive seed icon overlay per zone/bed | M1 – Setup | Medium | 1.5 | Not Started
Timeline Crop Map | Final Plot Overview | Page-Specific | Scrollable week timeline with crop icons per zone | M1 – Setup | Medium | 1.5 | Not Started